## WBS
TaskId | Team | Epic | Task | TaskType | SubTask | SubTaskType | Status | Priority | PlannedPersonDay | PlannedStartDate | PlannedEndDate | PersonDay | StartDate | EndDate | Assignee | Description | Version | BlockedBy | Tags[Tag1] | PV | EV | AC | AccumulatedPersonDay | AccumulatedStartDate | AccumulatedEndDate
|  | MyEpic | [6 empty] | 0 | [10 empty] | 0 | 0 | 0 | 0
|  | MyEpic | MyTask | Task |  |  |  |  | 0 | [10 empty] | 0 | 0 | 0 | 0
|  | MyEpic | MyTask | Defect | MySubTask | SubTask |  |  | 1 | 2024-05-01 | 2024-05-02 |  |  |  | ichiro.yamada |  |  |  |  | 1 | 0 | 0 | 1 | 2024-05-01 | 2024-05-02
|  | MyEpic | MyTask | Defect | MySubTask2 | SubTask |  |  | 2 | 2024-05-02 | 2024-05-07 |  |  |  | ichiro.yamada |  |  |  |  | 2 | 0 | 0 | 3 | 2024-05-02 | 2024-05-07
|  | MyEpic | MyTask | Defect | MySubTask3 | SubTask |  |  | 3 | 2024-05-07 | 2024-05-10 |  |  |  | ichiro.yamada |  |  |  |  | 3 | 0 | 0 | 6 | 2024-05-07 | 2024-05-10
|  | MyEpic | MyTask2 | Task |  |  |  |  | 0 | [11 empty] | 0 | 0 | 0
|  | MyEpic | MyTask2 | Task | MySubTask2 | SubTask |  |  | 2.5 | 2024-05-01 | 2024-05-06 |  |  |  | jiro.suzuki |  |  |  |  | 2.5 | 0 | 0 | 2.5 | 2024-05-01 | 2024-05-06
|  | MyEpic | MyTask2 | Task | MySubTask3 | SubTask |  |  | 5 | 2024-05-06 | 2024-05-13 |  |  |  | jiro.suzuki |  |  |  |  | 5 | 0 | 0 | 7.5 | 2024-05-06 | 2024-05-13
|  | MyEpic | MyTask2 | Task | MySubTask3 | SubTask |  |  | 6 | 2024-05-01 | 2024-05-10 |  |  |  | - |  |  |  |  | 6 | 0 | 0 | 6 | 2024-05-01 | 2024-05-10
Formulas:
AccumulatedStartDate = IF(WBS[[#This Row],[Assignee]]="", "", WORKDAY(master!$A3,WBS[[#This Row],[AccumulatedPersonDay]]-WBS[[#This Row],[PlannedPersonDay]]/master!$B3, Holiday[Holiday]))
AccumulatedEndDate = IF(WBS[[#This Row],[Assignee]]="", "", WORKDAY(master!$A3,WBS[[#This Row],[AccumulatedPersonDay]]/master!$B3, Holiday[Holiday]))
PlannedStartDate = WBS[[#This Row],[AccumulatedStartDate]]
PlannedEndDate = WBS[[#This Row],[AccumulatedEndDate]]

## master
■variables
StartDay | OvertimeRatePerDay(Default1)
2024-05-01 | 1
■master
Status | TaskType | SubTaskType | Priority | Assignee | Team | Version | Holiday
ToDo | Deliverable | Review | Highest | - | Team1 | v0.01 | 2024-04-29
Doing | Defect | FeedBack | High | ichiro.yamada |  |  | 2024-05-03
UnderReview | Issue | SubTask | Medium | jiro.suzuki |  |  | 2024-05-04
Done | ToDo |  | Low |  |  |  | 2024-05-05
| Task |  | Lowest